DIGITAL LOAN ORIGINATION SYSTEM

Project Charter

| Project | Digital Loan Origination System (LOS) |
| --- | --- |
| Document Version | 1.0 |
| Author | Gourav (Business Analyst) |
| Status | Approved |
| Reference | Sponsor: Head of Retail Lending |

# 1. Project Purpose

To digitize the personal loan application and decisioning process, reducing turnaround time from 5–7 business days to under 24 hours, by launching an online application portal integrated with an automated credit bureau check.

# 2. Objectives

- Reduce loan application turnaround time to under 24 hours for 80% of applications

- Increase application volume by 30% within the first 6 months by removing branch-visit friction

- Reduce manual credit-check effort for loan officers by automating credit bureau lookups

# 3. Scope Summary

In scope: Online application submission, digital KYC upload, automated credit score fetch (with configurable risk threshold), loan officer review/decision workflow, applicant notifications, MIS reporting.

Out of scope: Secured loans, disbursement and repayment tracking, core banking integration (Phase 2).

# 4. Milestones

| Milestone | Target Date |
| --- | --- |
| Requirement sign-off (BRD/FRD) | Week 2 |
| Credit Bureau API integration complete | Week 6 |
| Design & development complete | Week 9 |
| UAT | Week 11 |
| Go-live | Week 12 |

# 5. Budget

Budget approved under the bank's FY26 digital lending initiative. Detailed cost breakdown maintained separately by the PMO.

# 6. Key Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Credit Bureau API integration delay | High | Finalize vendor contract and sandbox access by Week 2 |
| Low applicant adoption at launch | Medium | In-app and SMS awareness campaign at launch |
| Regulatory/compliance gaps in digital lending | High | Legal and compliance review before go-live |
| Credit bureau vendor takes 3–4 weeks to provision API access post contract sign-off, threatening the Week 6 milestone | High | IT Head to expedite vendor contracting (tracked in MOM, 14-Jul-2026) |

Risk row 4 added to reflect a scheduling risk raised in the 14-Jul-2026 requirement review meeting that was not captured in the original charter.

# 7. Stakeholders

- Head of Retail Lending — Sponsor

- IT Head — Technical Approver

- Business Analyst — Requirements & coordination

- Loan Officers, Applicants — End Users

# 8. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Business Analyst | Gourav |  |  |
| Project Sponsor |  |  |  |
| IT Head |  |  |  |