DIGITAL LOAN ORIGINATION SYSTEM

Project Status Report

| Project | Digital Loan Origination System (LOS) |
| --- | --- |
| Reporting Period | 07-Jul-2026 to 14-Jul-2026 |
| Prepared By | Gourav (Business Analyst) |
| Overall Status | On Track |

# 1. Summary

The project remains on track for the Week 12 go-live target. BRD has been signed off and FRD is being updated to include a configurable risk threshold. Credit bureau vendor contracting is the primary item on the critical path.

# 2. Milestone Status

| Milestone | Target Date | Status |
| --- | --- | --- |
| BRD Sign-off | Week 2 | Completed |
| FRD Sign-off | Week 3 | In Progress |
| Credit Bureau API Integration | Week 6 | Not Started |
| Design & Development Complete | Week 9 | Not Started |
| UAT | Week 11 | Not Started |
| Go-live | Week 12 | Not Started |

# 3. Completed This Week

- BRD v1.0 signed off by Head of Retail Lending and IT Head

- Use case document and user stories drafted

- Wireframe for the loan application screen shared for feedback

# 4. Planned Next Week

- Finalize FRD with the configurable risk threshold (FR-02.4)

- Expedite credit bureau vendor contract

- Begin process flow validation with the Loan Officer team

# 5. Risks / Blockers

| Risk/Blocker | Impact | Mitigation / Owner |
| --- | --- | --- |
| Credit bureau vendor contract pending sign-off | High — may delay Week 6 integration milestone | IT Head to escalate by 21-Jul-2026 |